## Revision History
Genus Innovation Limited
Template Version -5
Refer Estimation guidelines for details on using this template.

## LFC Dist
LFC | EST | Column1
Requirements development | 15 | 0.061983
Planning | 12 | 0.049587
Design & Implementation | 100 | 0.41322
Validation | 100 | 0.41322
Overheads | 15 | 0.061983

## Complexity Estimation
Need ID | NEED Statement(VOC) | Algorithmic complexity | New Hardware and Firmware modules interfacing | Real time constraints and ISR | Reusability | External interfaces | Any Other factors | Comments/ Remarks if any | Complexity Score | Final Complexity
1 | Genus | 3 | 7 | 2 | 3 | 8 |  |  | 4.6 | M
1.1 | Solar
1.2 | UPS
Note on K2: where L is 1-3 M is >3 to <=7 and H is >7 to <=10

## DI Effort for Sample
Firmware
Req ID | 1
Requirement statement | Genus
req rating | M | Final Efforts | 10
| Variance | 0% |  | 0% |  | 0%
| ROUND 1 |  | ROUND 2 |  | ROUND 3
Paricipant name | Efforts R1 | Assumption r1 | Efforts R2 | Assumption R2 | Efforts R3 | Assumption R3
person a | 10
person b | 10
person c | 10
Total | 10 |  | 0 |  | 0
Req ID | 1
Requirement statement | Genus
req rating | M | Final Efforts | 0
| Variance | 0% |  | 0% |  | 0%
| ROUND 1 |  | ROUND 2 |  | ROUND 3
Paricipant name | Efforts R1 | Assumption r1 | Efforts R2 | Assumption R2 | Efforts R3 | Assumption R3
person a
person b
person c
Total | 0 |  | 0 |  | 0
Req ID | 1
Requirement statement | Genus
req rating | M | Final Efforts | 0
| Variance | 0% |  | 0% |  | 0%
| ROUND 1 |  | ROUND 2 |  | ROUND 3
Paricipant name | Efforts R1 | Assumption r1 | Efforts R2 | Assumption R2 | Efforts R3 | Assumption R3
person a
person b
person c
Total | 0 |  | 0 |  | 0
9.87

## Final Estimation-FRW
Final Estimations
Project Code
| Total days | 3.175
| Total working hours | 25.4
Participants
| Design & Implemenation Effort required for 1 Low complexity requirement in this project | L | 10
| Design & Implemenation Effort required for 1 Medium complexity requirement in this project | M | 20
| Design & Implemenation Effort required for 1 High complexity requirement in this project | H | 30
Need ID | NEED Statement(VOC) | Complexity Estimate | Estimated Design and Implementation effort | Final Agreed Estimates | Requirements Development | Planning | Design & Implementation
1 | Genus | M | 20 | 20 | 3 | 2.4 | 20
1.1 | Solar |  | 0 | 0 | 0 | 0 | 0
1.2 | UPS |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0
Total |  |  |  | 20 | 3 | 2.4 | 20
Note on D9: Wide band delphi, documented. Use values from DI effort for sample sheet
Note on E14: Change as needed. Add a comment whereever change is made to the calculated estimation, clearly mentioning the reason for change.