## Definitions
Master List of Configurable Items
Definitions:
Configuration Items (CI) – A “configuration item” is an entity designated for configuration management, which may consist of multiple related work products that form a baseline. This logical grouping provides ease of identification and controlled access. Configuration items can be individually managed and versioned, and they are usually treated as self-contained units for the purposes of identification and change control. All configuration items are uniquely identified by names, version numbers, and other attributes.
Baseline - A set of specifications or work products that has been formally reviewed and agreed on, which thereafter serves as the basis for further development, and which can be changed only through change control procedures. A change to a baseline is made with a change request because it is likely to involve new agreements or contracts with other affected groups. It may also have an effect on work that has already been completed in working from the original baseline.
Controlled Configuration Items- Controlled Configuration Items are those, whose current version in use is known (i.e. version control), and changes are recorded maintaining a version history.

## List of CI
List of Configurable Items (CI)
Sr. No. | Configurable Item Name | Type of CI | Trigger for Baselining | Responsibility for baselining | Triggers for basline revision*
1 | Customer's Requirements | Baselined | End of RD phase | Project Manager | Requirements Change Requests
2 | Functional Specifications | Baselined | End of RD phase | Project Manager | Requirements Change Requests
3 | Requirements Traceability Table | Controlled, Baselined at Project closure | Project Closure | NA | NA
4 | Requirements Evaluation Checklist | Controlled | NA | NA | NA
5 | Project plan | Baselined | End of Planning Phase | Project Manager | See Entry Criteria/Triggers of Planning Procedure
6 | Final Consolidated Estimates | Baselined | End of Planning Phase | Project Manager | Requirements Change Requests
7 | Plan Review Checklist | Controlled | NA | NA | NA
8 | Design documents (Firmware. Hardware and Mechanical) | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
9 | Interface Control and Integration Design Document | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
10 | Hardware Design Review checklist | Controlled | NA | NA | NA
11 | Firmware Design Review checklist | Controlled | NA | NA | NA
12 | Mechanical Design Review checklist | Controlled | NA | NA | NA
13 | Master Firmware Library | Baselined | End of Design & Implementation Phase | Functional Head | Identification of new reusable components
14 | Master Hardware Library | Baselined | End of Design & Implementation Phase | Functional Head | Identification of new reusable components
15 | Master Mechanical Library | Baselined | End of Design & Implementation Phase | Functional Head | Identification of new reusable components
16 | Schematic | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
17 | PCB layout | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
18 | Mechanical Drawing | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
19 | Source Code | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
20 | Bill of Material (BOM) | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
21 | Hardware Module Test Cases | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
22 | Firmware Module Test Cases | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
23 | Mechanical Module Test Cases | Baselined | End of Design & Implementation Phase | Project Manager | Requirements Change Requests, Defects detected downstream
24 | Integration Test Cases | Baselined | End of Integration Phase | Project Manager | Defects detected at validation phase
25 | System Test Cases | Baselined | End of Validation Phase | Project Manager | Defects detected during release
26 | Test Cases Checklist | Controlled | NA | NA | NA
27 | Project's Minutes of Meetings (MOM) | Controlled | NA | NA | NA
28 | Timesheet | Controlled | NA | NA | NA
29 | Audit Checklists | Controlled | NA | NA | NA
30 | Incident Management | Controlled | NA | NA | NA
31 | Incident Learnings | Controlled | NA | NA | NA
32 | Change Requests | Baselined | When Implemented/closed | Project Manager | Requirements Change Requests, Defects detected downstream
33 | DAR Documents | Baselined | Project Plan Approval | Project Manager | Identification of a critical decision
34 | Metrics report | Controlled, Baselined at Project closure | Project Closure | Project Manager | NA
35 | Project E-mails | Controlled | NA |  | NA
36 | Release note | Baselined | Project Closure | Project Manager | Defects detected after release
37 | Closure Report | Baselined | Project Closure | Project Manager | Defects detected after release
38 | PEG Plan | Baselined | Plan Approval | PEG Head | Significant deviation in schedule
39 | Metrics Baseline Report (MBR) | Baselined | MBR Release | PEG Head
40 | Quality Management System (QMS) | Baselined | QMS Release | PEG Head | Refer Process Improvement Procedure
41 | Measurement Repository | Baselined | MBR Release | PEG Head | Defects detcted in validation log.
42 | Policy | Baselined | QMS Release | PEG Head
43 | Business Objective to Process Objective document (BOTOPO) | Baselined | QMS Release | PEG Head
44 | Skill Matrix | Controlled | NA | NA | NA
45 | PPQA Annual Plan | Baselined | Plan Approval | PPQA Head | Significant deviation in plan
46 | Audit Reports | Controlled | NA | NA | NA
47 | PPQA Minutes of Minutes (MOM) | Controlled | NA | NA | NA
48 | PPQA Plan Review Records | Controlled | NA | NA | NA
49 | Audit Checklists | Controlled | NA | NA | NA
50 | Training Strategic Plan | Baselined | Plan Approval | Training coordinator | Identification of new training needs
51 | Training Calander | Controlled | NA | NA | NA
52 | Training Need Analysis | Baselined | Plan Approval | Training coordinator | Identification of new training needs
53 | Training Database | Controlled | NA | NA | NA
54 | Training Records | Controlled | NA | NA | NA
55 | Backup and Restoration Plans | Baselined | Plan Approval | IT Team | Change in infrastructure, Significant deviations from Plan
56 | Restoration Testing Records | Controlled | NA | NA | NA
57 | Backup | Baselined | As per Backup Plan | IT Team | As per Backup Plan
58 | QMS Change Requirements | Controlled | NA | NA | NA
59 | Senior Mangement Agenda List for PPQA Group | Controlled | NA | NA | NA
60 | PEG's Minutes of Meetings (MOM) | Controlled | NA | NA | NA
*The triggers are in addition to any defects detected after baselining. A valid defect report would be considered as a change request.

## Role Based Access Rights
Role Based Access Rights
R = Read
RW = Read Write
NA = No Access
Configurable Item Name | Design Head/Sr Mgmt | Project Manager | Functional Head | Developers | Verification Team | Validation Team | Audit Team | Training Coordinator | PEG | Configuration Administrator | IT Team
Customer's Requirements | R | RW | R | R | R | R | R | NA | NA | NA | RW
Functional Specifications | R | RW | RW | R | R | R | R | NA | NA | NA | RW
Requirements Traceability Table | R | RW | RW | RW | R | RW | R | NA | NA | NA | RW
Requirements Evaluation Checklist | R | R | R | R | RW | NA | R | NA | NA | NA | RW
Project plan | R | RW | R | NA | NA | NA | R | NA | NA | NA | RW
Final Consolidated Estimates | R | RW | R | NA | NA | NA | R | NA | NA | R | RW
Plan Review Checklist | R | R | NA | NA | RW | NA | R | NA | NA | R | RW
Design documents (Firmware. Hardware and Mechanical) | R | R | RW | R | R | R | R | NA | NA | R | RW
Interface Control and Integration Design Document | R | R | RW | R | R | R | R | NA | NA | R | RW
Hardware Design Review checklist | R | R | R | R | RW | R | R | NA | NA | R | RW
Firmware Design Review checklist | R | R | R | R | RW | R | R | NA | NA | R | RW
Mechanical Design Review checklist | R | R | R | R | RW | R | R | NA | NA | R | RW
Master Firmware Library | R | R | RW | R | NA | NA | R | NA | NA | R | RW
Master Hardware Library | R | R | RW | R | NA | NA | R | NA | NA | R | RW
Master Mechanical Library | R | R | RW | R | NA | NA | R | NA | NA | R | RW
Schematic | R | R | R | RW | R | NA | R | NA | NA | R | RW
PCB layout | R | R | R | RW | R | NA | R | NA | NA | R | RW
Mechanical Drawing | R | R | R | RW | R | NA | R | NA | NA | R | RW
Source Code | R | R | R | RW | R | NA | R | NA | NA | R | RW
Bill of Material (BOM) | R | R | RW | R | R | NA | R | NA | NA | R | RW
Hardware Module Test Cases | R | R | RW | RW | RW | NA | R | NA | NA | R | RW
Firmware Module Test Cases | R | R | RW | RW | RW | NA | R | NA | NA | R | RW
Mechanical Module Test Cases | R | R | RW | RW | RW | NA | R | NA | NA | R | RW
Integration Test Cases | R | R | RW | RW | RW | NA | R | NA | NA | R | RW
System Test Cases | R | R | R | R | R | RW | R | NA | NA | R | RW
Test Cases Checklist | R | R | R | R | RW | R | R | NA | NA | R | RW
Project's Minutes of Meetings (MOM) | R | RW | R | R | R | R | R | NA | NA | R | RW
Timesheet | RW | RW | RW | RW | RW | RW | RW | NA | NA | R | RW
Audit Checklists | R | R | R | R | R | R | RW | R | R | R | RW
Incident Management | RW | RW | RW | RW | RW | RW | RW | RW | RW | RW | RW
Incident Learnings | R | RW | RW | R | R | R | R | R | R | R | RW
Change Requests | R | RW | RW | RW | RW | RW | R | NA | NA | R | RW
DAR Documents | R | RW | RW | R | R | R | RW | RW | RW | RW | RW
Metrics report | R | RW | NA | NA | NA | NA | R | NA | R | R | RW
Release note | R | RW | R | R | R | R | R | NA | NA | R | RW
Closure Report | R | RW | R | R | R | R | R | NA | NA | R | RW
PEG Plan | R | NA | NA | NA | NA | NA | R | NA | RW | NA | RW
PEG's Minutes of Minutes (MOM) | R | NA | NA | NA | NA | NA | R | NA | RW | NA | RW
Metrics Baseline Report (MBR) | R | NA | NA | NA | NA | NA | R | NA | RW | NA | RW
Quality Management System (QMS) | R | R | R | R | R | R | R | R | RW | NA | RW
Measurement Repository | R | NA | NA | NA | NA | NA | R | NA | RW | NA | RW
Policy | RW | R | R | R | R | R | R | R | RW | R | RW
Business Objective to Process Objective document (BOTOPO) | RW | R | R | R | R | R | R | R | RW | R | RW
Skill Matrix | RW | R | RW | R | R | R | R | RW | RW | R | RW
PPQA Annual Plan | R | R | R | R | R | R | RW | R | R | R | RW
Audit Reports | R | R | R | R | R | R | RW | R | R | R | RW
PPQA Minutes of Minutes (MOM) | R | R | R | R | R | R | RW | R | R | R | RW
PPQA Plan Review Records | R | R | R | R | R | R | RW | R | R | R | RW
Audit Checklists | R | R | R | R | R | R | RW | R | R | R | RW
Training Strategic Plan | R | NA | NA | NA | NA | NA | R | RW | R | R | RW
Training Calander | R | NA | NA | NA | NA | NA | R | RW | R | R | RW
Training Need Analysis | R | NA | NA | NA | NA | NA | R | RW | R | R | RW
Training Database | R | NA | NA | NA | NA | NA | R | RW | R | R | RW
Training Records | R | NA | NA | NA | NA | NA | R | RW | R | R | RW
Backup and Restoration Plans | R | NA | NA | NA | NA | NA | R | NA | NA | NA | RW
Backup | NA | NA | NA | NA | NA | NA | R | NA | NA | NA | RW
QMS Change Requirements | NA | NA | NA | NA | NA | NA | R | NA | RW | NA | RW
Audit Schedule | R | R | NA | NA | NA | NA | RW | NA | NA | NA | RW
Senior Mangement Agenda List for PPQA Group | R | RW | NA | NA | NA | NA | RW | NA | NA | NA | RW