## Revision History
Genus Innovation Limited
Project Audit Checklist
Template Version - 6

## Initiation & RD-RM
Audit Checklist for Requirements Phase End
Project Code
Auditor
Auditee
Date
S. No | Checkpoint | Functional Non-Conformance/ Non-Functional Non-Conformance/ Observation | Log ID
PROJECT INITIATION
1 | Is the evidence of having received customer requirements upfront available( either as an archived email or otherwise)?
2 | Has a Project manager been formally appointed and the communication of the same archived?
3 | Has/Have the Customer Inputs been verified for adequacy and completeness by the project manager?
4 | Have the preplanning activities been performed(FS and kickoff dates, efforts etc.)?
5 | Has the project team been formally appointed and the communication of the same archived?
6 | Does the kickoff adequately address all project related concerns and important issues?
7 | Has the preliminary effort been estimated at project start?
REQUIREMENTS DEVELOPMENT AND MANAGEMENT
1 | Have the customer requirements been studied and analyzed in detail by the technical staff? Have appropriate and sufficient elaborations been made to the customer requirements?
2 | Have the clarifications sought from the customer been logged and tracked regularly?
3 | Has the meeting for requirements clarifications with the customer been conducted and documented?
4 | Has the functional specifications document been prepared?
5 | Have the requirements been reviewed using Requirement Review Checklist?
6 | Have the review findings been logged in the Incident Management?
7 | Have all review findings been closed suitably?
8 | Has the RTT been updated with the approved requirements?
9 | Has the RTT been reviewed by the Project manager and the findings logged in the Incident Management? Have the findings been closed suitably?
PMC
1 | Have the appropriate number of team meetings been conducted, documented and archived?
2 | Have the action Items from the team meetings conducted been noted in the MOM?
3 | Have the proposed tailorings been approved by the PEG?
4 | Are all action items identified, traceable to discussions?
5 | Are all team members relevant to the discussion point present?
6 | Are all action items tracked to closure?
7 | Are the pending action items in agenda items in all meetings?
8 | Are the issues as stated appropriate and to the point?
9 | Has the independent SME review been conducted?
10 | Have the findings of independent SME review been closed?
11 | Have all logs been updated on GIL.ef?
12 | Has the metrics report been prepared?
CM
1 | Have the Customer Inputs been placed under configuration management?
2 | Has the kickoff meeting been conducted and the minutes of meeting of the same archived?
3 | Has the projects configuration library been created and configured properly?
4 | Does the Project Configuration library have proper access rights and workflows configurations?
5 | Has the approval of the Functional specifications been taken from the customer?
6 | Have all the related artifacts such as the RTT, FS etc been placed under configuration control?
7 | Has the functional specifications document been baselined?
8 | Are all identified configurable items stored at their designated places?

## Planning
Audit Checklist for Planning Phase End
Project Code
Auditor
Auditee
Date
S. No | Checkpoint | Functional Non-Conformance/ Non-Functional Non-Conformance/ Observation | Log ID
1 | Has the project plan been established using as per the defined and current on GIL.ef & Project Plan template?
2 | Have the proposed tailorings been approved by the PEG?
3 | Has the Risk management plan been prepared for identification and mitigation of project risks and identification & leverage of Project Opportunities?
4 | Has the project Schedule been prepared?
5 | Has the test Plan been prepared?
6 | Has DAR been applied appropriately for planning decisions?
7 | Is the problem statement for DAR clear and concise?
8 | Is the decision arrived at using DAR clearly stated and uses sound judgment?
9 | Have the actions required for contingency and mitigation of the identified risks been properly listed?
10 | Has the plan been reviewed?
11 | Has the Plan review checklist been used for the review and the same archived? Verify the plan with respect to the populated review checklist on a sampling basis.
12 | Have the review findings of the plan been logged in the Incident Management?
14 | Has the plan been approved by Senior Management?
15 | Are the projects measurement targets appropriately determined with due consideration of project needs?
16 | Has the Complexity factor been determined appropriately using all relevant factors?
17 | Is the rationale to modify the calculated design and implementation effort documented and satisfactory?
18 | Has the preliminary effort been estimated at project start?
19 | Has the preliminary effort been considered in calculating effort variance at the end of RD phase and the same specified in Metrics report?
20 | Has the project schedule been initiated at project start mentioning all RD activities?
21 | Are all planned tasks such as training, reviews, tracking, audit etc. been captured and planned for in Schedule?
22 | Are the talent maps and gaps identified?
23 | Does the training plan cover the training activities adequately such as trainer's name, duration , audiences etc.
24 | Are corrective actions identified for metrics outside the decided thresholds?
25 | Has the independent SME review been planned covering reviewer, reviewed, and the artefacts selected as per project needs?
26 | Are the identified risk sources and risk categories appropriate?
27 | Are the rationale for large RPN revisions stated clearly?
28 | Are the mitigation plans appropriate for the risk under consideration?
29 | Are the contingency plans appropriate for the risk under consideration?
30 | Are all critical project and milestone deliverables selected for review? Eg. User Manual
31 | Are all critical project and milestone deliverables selected for validation?
32 | Has the approved plan intimation mail been done to all relevant stakeholders?
33 | Has the Project's Financials identified clearly?
34 | Has the Project's Assests, Knowledge & Technology identified clearly?
PMC
1 | Has the metrics report been prepared?
2 | Has the metrics report been reviewed
3 | Have the appropriate number of team meetings been conducted, documented and archived? Do they cover all planning parameters including project measures and issues?
4 | Have the action Items from the team meetings conducted been noted in the MOM?
5 | Has the milestone review of the phase end been conducted with the senior management?
6 | Have the action Items from the milestone reviews conducted been noted in the MOM?
7 | Has the Project schedule been updated?
8 | Are the projects backups being taken at the defined frequency?
9 | Have the proposed tailorings been approved by the PEG? Are tailoring approver and requester independent?
10 | Are all action items identified, traceable to discussions?
11 | Are all action items derived using discussions?
12 | Are all team members relevant to the discussion point present?
13 | Are all action items tracked to closure?
14 | Are the pending action items in agenda items in all meetings?
15 | Are the issues as stated appropriate and to the point?
16 | Has the independent SME review been conducted?
17 | Have the findings of independent SME review been closed?
18 | Are all identified configurable items stored at their designated places?
19 | Have all the non-functional NCs of previous stage closed?
20 | Have all logs been updated on GIL.ef?
CM
1 | Has the plan been placed under Configuration management?
2 | Are all project and milestone deliverables identified as configurable items?
3 | Is the versioning workflow properly set up on the CM tool?
4 | Are all relevant project artefacts under appropriate levels of configuration control?
5 | Has the metrics report been placed under configuration management?

## Design-Implementation
Audit Checklist for Design and Implementation Phase End
Project Code
Auditor
Auditee
Date
S. No | Checkpoint | Functional Non-Conformance/ Non-Functional Non-Conformance/ Observation | Log ID
1 | Has the Design documents been prepared as per the defined and current Design template?
2 | Have the Design documents been reviewed?
3 | Has all interfaces idenfied?
4 | Has all Interfaces been reviewed?
5 | Has the RTT been updated?
6 | Has the RTT been reviewed?
7 | Are all the external interfaces designed in the Design phase clearly traceable and marked as such in the functional specification?
8 | Has DAR been applied appropriately for critical design decisions? (If DAR applied)
9 | Is the problem statement for DAR clear and concise?
10 | Is the decision arrived at using DAR clearly stated and use sound judgment?
11 | Have the findings of the reviews conducted logged in Incident Management?
12 | Has the Design been approved by the project manager?
13 | Have the respective modules been allocated to individual developers and the plan updated suitably?
14 | Are all reused components available in Master list of libraries?
15 | Have the reuse components generated in the project been included in Master list of library?
16 | Is the rationale of choosing off the shelf and internal reusable components documented?
17 | Has the design documents been reviewed with respect to requirement? (QA should sample at least one requirement and try tracking its design)
18 | Have the findings of the reviews conducted logged in Incident Management?
19 | Have the Test cases been developed?
20 | Have the Test Cases been reviewed?
21 | Are the test types in the test plan traceable to their respective test cases?
22 | Has testing been conducted and the findings logged in Incident Management?
23 | Have corrective actions been identified and tracked to closure for the defects identified in reviews and testing?
24 | Has the defects analysis done?
PMC
1 | Has the metrics report been prepared?
2 | Has the metrics report been reviewed?
4 | Have the appropriate number of team meetings been conducted, documented and archived? Do they cover all planning parameters including project measures?
5 | Have the action Items from the team meetings conducted been noted in the MOM?
6 | Has the milestone review of the phase end been conducted with the senior management?
7 | Have the action Items from the milestone reviews conducted been noted in the MOM?
8 | Has the Project plan been updated?
10 | Are all action items identified, traceable to discussions?
12 | Are all team members relevant to the discussion point present?
13 | Are all action items tracked to closure?
14 | Are the pending action items in agenda items in all meetings?
15 | Are the issues as stated appropriate and to the point?
16 | Has the independent SME review been conducted?
17 | Have the findings of independent SME review been closed?
18 | Are all identified configurable items stored at their designated places?
19 | Have the proposed tailorings been approved by the PEG? Are tailoring approver and requester independent?
20 | Have all the non-functional NCs of previous stage closed?
21 | Have all logs been updated on GIL.ef?
Requirements Changes
1 | Have the requirement changes requested been approved and agreed to formally?
2 | Has the impact of those changes over the project's products been analyzed?
3 | Have the functional specifications been revised and new baseline released?
4 | Has the RTT been updated?
5 | Has the plan been updated?
6 | has the updated plan been reviewed and approved?
7 | Have the necessary changes been made to the impacted artifacts?
CM
1 | Has the Design documents been placed under configuration control?
2 | Has the RTT been placed under configuration control?
3 | Are all relevant project artefacts under appropriate levels of configuration control?
4 | Has the metrics report been placed under configuration management?
5 | Are the projects backups being taken at the defined frequency?
6 | Has the Implemented design been baselined?
7 | Have the Test Cases been placed under configuration control?

## Integration
Audit Checklist for Integration Phase End
Project Code
Auditor
Auditee
Date
S. No | Checkpoint | Functional Non-Conformance/ Non-Functional Non-Conformance/ Observation | Log ID
1 | Have the integration steps been verified? Have the defects been logged in the Incident Management?
2 | Have all defects been closed?
3 | Has product support documentation and user manual been prepared?
4 | Have integration test cases been developed?
5 | Have the integration test cases been reviewed and the defects logged in Incident Management?
6 | Are the test types in the test plan traceable to their respective test cases?
7 | Have corrective actions been identified and tracked to closure for the defects identified in reviews and testing?
8 | Has the RTT been updated?
9 | Has the RTT been reviewed?
10 | Has the defects analysis done?
PMC
1 | Has the metrics report been prepared?
2 | Has the metrics report been reviewed
3 | Have the appropriate number of team meetings been conducted, documented and archived? Do they cover all planning parameters including project measures?
4 | Have the action Items from the team meetings conducted been noted in the MOM?
5 | Has the milestone review of the phase end been conducted with the senior management?
6 | Have the action Items from the milestone reviews conducted been noted in the MOM?
7 | Has the Project plan & schedule been updated?
8 | Are all action items identified, traceable to discussions?
9 | Are all action items derived using discussions been noted in the MOM?
10 | Are all team members relevant to the discussion point present?
11 | Are all action items tracked to closure?
12 | Are the pending action items in agenda items in all meetings?
13 | Are the issues as stated appropriate and to the point?
14 | Has the independent SME review been conducted?
15 | Have the findings of independent SME review been closed?
16 | Are all identified configurable items stored at their designated places?
17 | Have the proposed tailorings been approved by the PEG? Are tailoring approver and requester independent?
18 | Have all the non-functional NCs of previous stage closed?
19 | Have all logs been updated on GIL.ef?
Requirements Changes
1 | Have the requirement changes requested been approved and agreed to formally?
2 | Has the impact of those changes over the project's products been analyzed?
3 | Has the RTT been updated?
4 | Has the plan been updated?
5 | Has the updated plan been reviewed and approved?
6 | Have the necessary changes been made to the impacted artifacts?
CM
1 | Has the RTT been placed under configuration control?
2 | Are all relevant project artifacts under appropriate levels of configuration control?
3 | Has the metrics report been placed under configuration management?
4 | Have the functional specifications been revised and new baseline released?
5 | Are the projects backups being taken at the defined frequency?

## Validation and closure
Audit Checklist for Validation Phase End and Closure
Project Code
Auditor
Auditee
Date
S. No | Checkpoint | Functional Non-Conformance/ Non-Functional Non-Conformance/ Observation | Log ID
1 | Has the test schedule and environment been identified using the System Test Cases template?
2 | Has test plan been prepared?
3 | Have the above been reviewed and defecs logged in Incident Management?
4 | Have the test plan and system test cases been approved?
5 | Are the test types in the test plan traceable to their respective test cases?
6 | Has the RTT been updated?
7 | Has the RTT been reviewed?
8 | Has the validation environment been established?
9 | Has the product been validated and the defects logged in Incident Management?
10 | Have all defects been closed?
11 | Have corrective actions been identified and tracked to closure for the defects identified in reviews and testing?
12 | Has the validation report been issued?
13 | Has the defects analysis done?
Closure
1 | Has the closure report been prepared?
2 | Has the closure report been verified by the PPQA member?
3 | Has the project closure report been submitted to the PEG?
4 | Are the project learnings proposed in Incident learnings, actionable and specific?
5 | Have all NCs observed during project execution been closed?
PMC
1 | Has the metrics report been prepared?
2 | Has the metrics report been reviewed?
3 | Have the appropriate number of team meetings been conducted, documented and archived? Do they cover all planning parameters including project measures?
4 | Have the action Items from the team meetings conducted been noted in the MOM?
5 | Has the milestone review of the phase end been conducted with the senior management?
6 | Have the action Items from the milestone reviews conducted been noted in the MOM?
7 | Has the Project plan been updated?
8 | Are all action items identified, traceable to discussions?
9 | Are all action items derived using discussions been noted in the MOM?
10 | Are all team members relevant to the discussion point present?
11 | Are all action items tracked to closure?
12 | Are the pending action items in agenda items in all meetings?
13 | Are the issues as stated appropriate and to the point?
14 | Has the independent SME review been conducted?
15 | Have the findings of independent SME review been closed?
16 | Have the proposed tailorings been approved by the PEG? Are tailoring approver and requester independent?
17 | Have all the non-functional NCs of previous stage closed?
18 | Have all logs been updated on GIL.ef?
Requirements Changes
1 | Have the requirement changes requested been approved and agreed to formally?
2 | Has the impact of those changes over the project's products been analyzed?
3 | Has the RTT been updated?
4 | Has the plan been updated?
5 | has the updated plan been reviewed and approved?
6 | Have the necessary changes been made to the impacted artifacts?
CM
1 | Has the RTT been placed under configuration control?
2 | Is configuration auditor independent of the project team?
3 | Are all relevant project artifacts under appropriate levels of configuration control?
4 | Has the metrics report been placed under configuration management?
5 | Are all identified configurable items stored at their designated places?
6 | Are the projects backups being taken at the defined frequency?
7 | Have the functional specifications been revised and new baseline released?