## Revision History
Genus Innovation Limited
Template Version -8
Refer Estimation guidelines for details on using this template.

## Guidelines
Complexity Estimations | Firmware:
The estimation of complexity of a requirement is critical to estimating the project work against it for design, implementation, testing among other aspects. Expert judgment and historical information of similar activities is the basis for this estimation. If a particular requirement does not entail complexity in particular functional area, then complexity score would be zero (0) for the same. The tables below are complimentary to the practitioner’s expert judgment and project performance experience. The practitioner must take into account the following factors, among others, in determining the complexity of a certain requirement. The complexity score for each factor against an individual requirement is averaged. Based on the average, the tool assigns a score from LOW to HIGH to each requirement. | Complexity factor | High Complexity (8 - 10) | Medium Complexity (4 - 7) | Low Complexity (1 - 3)
| Algorithmic complexity | Intensive transformation including mathematical calculation, complicated decision flow | Complicated decision flow | No intensive transformation and complicated decision flow
| New Hardware and Firmware modules interfacing | More than 15 configuration registers with sensitive (5% variance) timing and sequencing constraints | More than 10 , less than 15 configuration registers with sensitive (10% variance) timing | Less than 5 configuration registers
Unfamiliar architecture
| Real time constraints and ISR | Sensitive timing constraints, High ISR frequency | High ISR frequency | No sensitive timing related constraints
| Reusability ( %) | 0 <= Reusability <= 30 | 30 < Reusability < = 70 | 70 < Reusability < = 100
| External interfaces | External hardware and Communication interface | External hardware interface | External communication interface
Hardware and PCB:
| Complexity factor | High Complexity (8 - 10) | Medium Complexity (4 - 7) | Low Complexity (1 - 3)
| Component characteristics and Packaging | More Than One ICs and five non-linear components. | Less than or equal to one IC. | Less than or equal to one non linear component
Less than or equal to five and more than one non-linear components
| Accuracy | Tolerance <= 2% | 2% < Tolerance < 5% | Tolerance >= 5%
| Longetivity | Warranty years >= 5 | 2<Warranty years < 5 | Warranty years <= 2
| No. of internal/external interfaces | External interfaces | External interfaces | External interfaces
|  | · Fitment | · Fitment | · Functional performance
|  | · User Safety | · Functional performance
|  | · Equipment safety | Internal interfaces with other daughter boards < 3
· Functional performance
Internal interfaces with other daughter boards >= 3
| EMI/EMC | More susceptibility to EMI/EMC | Less susceptibility to EMI/EMC | No susceptibility to EMI/EMC
| Analog/Digital | Analog plus digital | Analog | Digital
| PCB Layout | SMD Compnents <90% | SMD Compnents >=90% | 100% through hole components
| Reusability (%) | 0 <= Reusability <= 30 | 30 < Reusability < = 70 | 70 < Reusability < = 100
Mechanical:
| Complexity factor | High Complexity (8 - 10) | Medium Complexity (4 - 7) | Low Complexity (1 - 3)
| Aesthetic requirements | Highly user visible part | User serviceable part | Internal non-user visible part
| User handling, safety constraints and ergonomics | High frequency of handling, Risk of fatal Injury/death | Medium frequency of handling | Rarely used
| IPxy requirements and mechanical standard compliance (X) | X >= 5 | 2 < X < = 4 | X <= 2
| IPxy requirements and mechanical standard compliance (Y) | Y > 2 | 0 < Y <= 2 | Y = 0
| Precision and Tolerance | Tolerance <= 0.5mm | 0.5mm <Tolerance< 2.0mm | Tolerance >= 2.0mm
| Reusability ( %) | 0 <= Reusability <= 30 | 30 < Reusability < = 70 | 70 < Reusability < = 100

## Reference Projects Efforts
Final Estimations
Project Code
S. No. | Reference Project Name | Why Selected as Reference | Actual Efforts in Phase-1 | Actual Efforts in Phase-2 | Actual Efforts in Phase-3 | Actual Efforts in Phase-4 | Actual Efforts in Phase-5
1 | g123 | LCD display type/feature/PCB same; Chassis concept same; artworks concept same | 40 | 35 | 150 | 70 | 120
2 | g134 | Solar charger rating & PCB same; Chassis concept same; artworks concept same | 50 | 40 | 180 | 75 | 150
3
4
5
6
7
|  | Average Efforts in person hours | 45 | 37.5 | 165 | 72.5 | 135
| Difference from reference in detail | Impact in person hours due to the difference | Complexity | Remarks (Optional)
1 | Display module as it is reused from g123 | -50 | H | Only model name need to display via little modification in firmware
2 | Solar charger module as it is reused from g134 | -80 | H | Only fitment on new power need to fix
3 | Chassis size will increase to accommodate new modules like Power PCB, T/R | 100 | H | Chassis concept same with g123
4 | Terminal blocks, MCB locations & wiring/routing | 50 | M | During chassis design, integration this need to ensure more precisely
5 | Power PCB new design to incorporate TO-247 package MOSFETs, power tracks, spacious but compact | 100 | H | Totally new design, circuits concept same
6 | artworks like User manual, chassis stickers and screens | 20 | L | modified existing artworks to incorporate this model.
7
8
9
10
11
12
13
14
15
| Total Impact | 140
|  |  | Size | 4H+1M+1L
|  | Estimated Efforts in Phase-1 | Estimated Efforts in Phase-2 | Estimated Efforts in Phase-3 | Estimated Efforts in Phase-4 | Estimated Efforts in Phase-5
| Past Projects | 45 | 37.5 | 165 | 72.5 | 135
| Differences from reference projects | 14 | 12 | 51 | 22 | 42 | Total
| Final estimates | 59 | 49.5 | 216 | 94.5 | 177 | 596