## Revision History
Genus Innovation Limited
Template Version - 1

## Checklist
Plan Review Checklist
Project code:
Date:
Reviewer/s:
Author/s:
S. No | Checkpoint | Yes/No | Comments/ Findings
1 | Has the table of contents been updated?
2 | Has the template been renamed in conformance with the CM procedure?([ProjectCode_PRJPLN]
3 | Is the version of the template used current?
4 | Has the scope of the project been clearly identified?
5 | Has the vision of the project been clearly identified?
6 | Are the customer Request Date, Delivery schedule and Customer's identification been correctly captured?
7 | Is the product development lifecycle appropriate? Has it been referred from defined project lifecycle?
8 | Have the tailorings been proposed? In case of no tailorings, has it been clearly specified with no linkage to the tailoring proposals database? If tailorings have been proposed, are they approved using the standard mechanism?
9 | Have the final estimates been arrived at properly?
10 | Are the phase wise efforts in the Project plan in conformance with the ones arrived at in the final estimations sheet?
11 | Are the phase wise efforts in the Project plan in conformance with the projects schedule?
12 | Are NRE expenditures correctly gauged?
13 | Have all the hardware and software resources clearly mentioned?
14 | Has the project's schedule been prepared and linked to?
15 | Has the project been broken in appropriate tasks in the schedule?
16 | Have the project's training needs been identified in detail?
17 | Have the training requests been logged?
18 | Have the project's risks been uniquely mentioned and analysed?
19 | Are the risks documented in sufficient details?
20 | Has the master list of risks been referred in risk identification?
21 | Are the mitigation and contingency plans in place?
22 | have the RPN been calculated using proper risk ratings?
23 | Are the project's practitioners conversant with the identified risks and their implications?
24 | Have the project start audit, Project end audit and milestone audits been planned?
25 | Have the work product audits been planned with identification of work products?
26 | Are the workproducts to be reviewed identified in toto?
27 | Have the sr. mgmt reviews been planned?
28 | Have the metrices been identified?
29 | Are project deliverables in line with the customer's requirements?
30 | Have the references to CM guidelines/procedures/lists been retained?
31 | Has the project repository been hyperlinked?
32 | Has the current backup plan been linked to?
33 | Have the DAR activities been identified and stated clearly?
34 | Is the escalation section updated?
35 | Has the R&R matrix been filled?
36 | Has the plan been approved?
37 | Has it been place under Configuration management?